## Slide 1
Team Nexus:
Alexander Hall, Benjamin Dluzak, David Kopp, Raffi Nalbandian, Vahan Tokadjian, Phillip Tran

## Slide 2: Vision for Project Nexus
“To create a website that provides gamers with a social platform to interact with in-game character statistics, player made guides and additional information, and a way for players to find other individuals to play their favorite online games with.”

## Slide 3: Project Nexus Roadmap
Website Characteristics
  User Profiles
  Instant Messenger
  Discussion Forums
  User(s) Game Statistics
  Match Finder (Schedule Matching)
Environment
  Jetty Server
Development Languages / Tools
  Java, JavaScript, Maven, CSS, and HTML
  AngularJS, Java Spark, Eclipse, 0xDBE, and Brackets

## Slide 4: SLOC Production
Estimated SLOC:
  10 KLOC
Actual SLOC:
  3457 SLOC

## Slide 5: Risk Analysis
Lack of testing
  Mitigated by Junit testing
SCRUM and Communication Tool
  Mitigated by migrating to Trello and Slack
Scope too large
  Mitigated by de-scoping
  Removed group pages and email service

## Slide 6: PAL PangoScrum
http://csuncomp380.pangoscrum.com/products/18898

## Slide 7: Products Produced

## Slide 10
Chart: Project Nexus Product Burndown Chart
| Hours Sprint 1 | Hours Sprint 2 | Hours Sprint 3 | Hours Sprint 4 | Hours Sprint 5
Percent of Items Finished | 0 | 1 | 1 | 1 | 0.88889 | 0.85714
Actual Remaining Hours | 270 | 238 | 186 | 99 | 37 | 0
Estimated Remaining Hours | 270 | 216 | 162 | 108 | 54 | 0

## Slide 11: PAL GitHub
https://github.com/akatoshbla/Nexus

## Slide 12: PAL Google Group
Google Drive Hyperlink

## Slide 13: Process Retrospective
Worked Well
  Sprints
  Communication
  Retrospective Meetings
Did Not Work Well
  PangoScrum
  Testing
  Scope

## Slide 14: Changes for Next Semester
Trello
Slack
Unit Testing
Re-evaluate Project Scope

## Slide 15: Demo Incoming, Resistance is Futile