## Burn Down Chart Data
Task | Start Hours | Hours Sprint 1 | Hours Sprint 2 | Hours Sprint 3 | Hours Sprint 4 | Hours Sprint 5 | Total Hours
Server Setup | 6 | 6 | 0 | 0 | 0 |  | 6
Front End AngularJS | 22 | 8 | 8 | 4 | 8 |  | 28
User Login | 16 | 8 | 8 | 0 | 4 |  | 20
New User | 12 | 0 | 4 | 0 | 0 | 8 | 12
Middle Tier API | 22 | 8 | 10 | 8 | 4 |  | 30
Profile Page | 16 | 0 | 6 | 6 | 4 |  | 16
User Sessions | 12 | 0 | 8 | 8 | 0 |  | 16
Database Management | 8 | 0 | 2 | 2 | 2 |  | 6
Documentation | 12 | 2 | 2 | 2 | 1 | 5 | 12
LoL Game Page | 2 | 0 | 2 | 0 |  |  | 2
Front Page | 21 | 0 | 2 | 2 | 4 | 4 | 12
Front Page Template | 12 | 0 | 0 | 8 | 5 |  | 13
Settings Page | 0 | 0 | 0 | 0 | 0 |  | 0
Edit Friends List | 8 | 0 | 0 | 0 | 6 |  | 6
Game Content Pages | 0 | 0 | 0 | 0 | 0 |  | 0
Group Page | 0 | 0 | 0 | 0 | 0 |  | 0
Group Page Template | 0 | 0 | 0 | 0 | 0 |  | 0
Friend Finder Page | 0 | 0 | 0 | 0 | 0 |  | 0
Edit Friend Finder | 0 | 0 | 0 | 0 | 0 |  | 0
Friends List | 24 | 0 | 0 | 12 | 6 | 5 | 23
Profile Edits | 12 | 0 | 0 | 0 | 4 |  | 4
Instant Message Service | 8 | 0 | 0 | 10 | 2 | 0 | 12
User Profiles | 24 | 0 | 0 | 12 | 3 | 4 | 19
Group Profiles | 0 | 0 | 0 | 0 | 0 |  | 0
Game APIs | 0 | 0 | 0 | 0 | 0 |  | 0
Discussion Forums | 8 | 0 | 0 | 5 | 1 |  | 6
Front Page News feed | 12 | 0 | 0 | 8 | 8 |  | 16
Unit Testing | 13 | 0 | 0 | 0 | 0 | 13 | 13
Friend Finder Service | 0 | 0 | 0 | 0 | 0 |  | 0
Actual Remaining Hours | 270 | 238 | 186 | 99 | 37 | 0
Estimated Remaining Hours | 270 | 216 | 162 | 108 | 54 | 0
Sprint# | Number of Items | Number of Finished Items | Finished Percent | Total Items | Total Items Finished
Sprint0 | 0 | 0 | 0% | 35 | 33
Sprint1 | 4 | 4 | 100%
Sprint2 | 5 | 5 | 100%
Sprint3 | 10 | 10 | 100%
Sprint4 | 9 | 8 | 88.89%
Sprint5 | 7 | 6 | 85.71%